## Overview
Live view of the data tables in this workbook. Edit the numbers in the data sheets (after "Huong dan"); this page recalculates at once.
|  |  |  | CBTA development (CPP & WHP) | Mandatory training · offshore | Procedures · HSE ¦ general operations | PRs in progress
Current staffing
Filled / required positions at the report date.
Group | Filled | Required | Filled %

## Manpower & Training
Mandatory training, CBTA development and assessment, vendor training schedule.
Mandatory training – PQPOC offshore staff |  |  |  |  | CBTA by team: development and assessment
Courses completed vs required by the HSE training matrix. Red below 30%. |  |  |  |  | Modules developed and theory / OJT assessment progress.
Team | Planned | Earned | Balance | Completed % | Platform | Team | Modules | Completed | In dev. | In review | % developed | % theory | OJT modules | % OJT
Total
Vendor training schedule
Period = month (YYYY-MM) or year.
[5 empty] | Period |  | Course

## ORR
ORR checklist: group totals, progress by OPS team and by checklist element.
Gap = actual – plan, in percentage points. Red when behind plan.
Team |  | Weight | Activities | Completed | Plan % | Actual % | Gap (pts) | Final plan %
Checklist by element (People · Plant · Process)
Elements below 50% are shown in red.
Code | Element |  |  |  |  | Group | Items | Progress

## Procedures
Procedure completion. The full register is the "Quy trinh" data sheet; this page lists the ones still open.
Open procedures (not yet issued)
In register order. Red: 0% · amber: in progress.
Code | Document | Owner | Due | Completion | Remark

## Contracts & Permits
Tendering pipeline, packages without PR, applications, logistics and permit register.
PRs in progress by stage | [5 empty] | Packages without PR |  |  |  | CMMS (OA) – actual vs plan
Count by schedule status. Stage names must match the "PR dang xu ly" data sheet.
Stage | Late | Near-late | On time | Total |  | Procurement status |  | Packages |  | Package | Actual | Plan | Gap (pts)
1 CSP Preparation
2 CSP Approval
3 Bidding
4 Evaluation
5 TCEAR Approval
6 Contract Signing
[6 empty] | Priority |  | Packages
[6 empty] | Expected SCR |  | Packages
Applications | [6 empty] | Logistics, services & coordination
Item | Status | [5 empty] | Item |  | Status
Offshore platform permit register
Red: waiting · amber: temporary · green: issued.
Permit |  |  | Applies to |  | Authority | Issued | Expires | Renew by | Status

## Commissioning
CPP pre-commissioning plan by week. Green: done (actual finish entered) · red: in its window on the report date · blue: planned.
Report date
First week
Activity | Plan start | Plan finish | Actual finish
Preservation, installation & commissioning
Item | Status
CPP start-up sequence
Summarised from the CPP start-up block diagram.
Step · phase | Action

## Huong dan
OPS DASHBOARD – FILE SỐ LIỆU NGUỒN
Cách dùng
1. Mỗi sheet là một bảng (Excel Table). Chỉ sửa số liệu trong bảng; thêm dòng bằng cách gõ ngay dưới dòng cuối của bảng (bảng tự mở rộng).
2. KHÔNG đổi tên bảng (Table Design → Table Name), KHÔNG đổi tên cột ở dòng tiêu đề. Dashboard đọc theo đúng các tên này.
3. Ngày tháng gõ dạng chữ: tháng YYYY-MM (2026-11), ngày YYYY-MM-DD (2026-11-30). Các cột ngày đã định dạng Text sẵn.
4. Phần trăm gõ số 0–100 (ví dụ 70.5), không gõ dấu %. Ô chưa có số để trống.
5. Power Automate đọc file này theo lịch và đẩy lên dashboard. Sau khi lưu, chờ tới lượt chạy kế tiếp (hoặc chạy tay luồng) rồi 1–2 phút để Vercel cập nhật.
6. Các sheet dashboard (Overview … Commissioning) ở đầu file tự tính lại ngay khi sửa số; không cần sửa gì trên các sheet đó.
Bảng | Sheet | Hiển thị ở | Cột | Ý nghĩa
meta | Thong tin | Ngày báo cáo và tiêu đề (1 dòng duy nhất) | report_date | Ngày báo cáo, dạng YYYY-MM-DD
|  |  | report_title | Tên báo cáo
|  |  | prepared_by | Đơn vị lập
manpower | Nhan su theo thang | Biểu đồ tăng cường nhân sự; KPI nhân sự lấy tháng cuối cùng có số thực tế | month | Tháng, dạng YYYY-MM
|  |  | onshore_plan | Onshore kế hoạch
|  |  | onshore_actual | Onshore thực tế (để trống nếu chưa tới)
|  |  | offshore_plan | Offshore kế hoạch
|  |  | offshore_actual | Offshore thực tế
|  |  | total_plan | Tổng kế hoạch
|  |  | total_actual | Tổng thực tế
staffing | Dinh bien | Thẻ "Định biên hiện tại" | group | Nhóm
|  |  | filled | Đã có
|  |  | required | Cần
cbta | CBTA | Tab Nhân sự & đào tạo: CBTA | platform | CPP hoặc WHP
|  |  | team | Team
|  |  | modules | Tổng module
|  |  | developing | Đang biên soạn
|  |  | review | Đang soát xét
|  |  | completed | Đã hoàn thành
|  |  | theory_pct | % đánh giá lý thuyết (0–100)
|  |  | ojt_modules | Số module OJT
|  |  | ojt_pct | % đánh giá OJT (0–100)
mandatory | Dao tao bat buoc | Đào tạo bắt buộc offshore | team | Team
|  |  | planned | Số khoá kế hoạch
|  |  | earned | Số khoá đã hoàn thành
|  |  | balance | Còn lại
vendor_training | Dao tao vendor | Lịch đào tạo vendor | course | Tên khoá
|  |  | period | Tháng YYYY-MM, hoặc chỉ năm YYYY
orr_teams | ORR theo team | ORR theo team OPS (tháng hiện tại) | team | Team
|  |  | weight_pct | Trọng số %
|  |  | total_activities | Tổng hoạt động
|  |  | completed | Đã hoàn thành
|  |  | plan_pct | % kế hoạch tháng hiện tại
|  |  | actual_pct | % thực tế tháng hiện tại
|  |  | plan_end_pct | % kế hoạch cuối kỳ
orr_curve | ORR theo thang | Đường ORR kế hoạch/thực tế; KPI ORR lấy tháng cuối cùng có thực tế | month | Tháng YYYY-MM
|  |  | plan_pct | % kế hoạch tổng
|  |  | actual_pct | % thực tế tổng (để trống nếu chưa tới)
orr_elements | ORR hang muc | Bảng checklist theo hạng mục | group | PEOPLE / PLANT / PROCESS
|  |  | code | Mã (không trùng)
|  |  | element | Tên hạng mục
|  |  | items | Số đầu mục
|  |  | progress_pct | % tiến độ (0–100)
orr_groups | ORR tong nhom | Ô tổng ORR theo nhóm | group | PEOPLE / PLANT / PROCESS / TOTAL (giữ nguyên tên)
|  |  | items | Số đầu mục
|  |  | progress_pct | % tiến độ (0–100)
procedures | Quy trinh | Tab Quy trình | id | Mã (không trùng, ví dụ HSE-41)
|  |  | category | "HSE" hoặc "General operations" (giữ đúng chữ)
|  |  | document | Tên tài liệu
|  |  | level | Company / Department
|  |  | issued | "Yes" nếu đã ban hành, "No" nếu chưa
|  |  | responsible | Người phụ trách
|  |  | expected | Hạn, ví dụ Dec-26
|  |  | completion_pct | % hoàn thành (0–100)
|  |  | remark | Ghi chú
packages_no_pr | Goi chua co PR | Gói chưa có PR | dimension | status / priority / scr_timing (giữ nguyên)
|  |  | category | Nhóm
|  |  | count | Số gói
pr_pipeline | PR dang xu ly | PR theo bước | stage | Bước (giữ số thứ tự ở đầu)
|  |  | status | "Late", "Near-late" hoặc "On time" (giữ đúng chữ)
|  |  | count | Số PR
cmms | CMMS | CMMS (OA) | package | Gói
|  |  | actual_pct | % thực tế
|  |  | plan_pct | % kế hoạch
workstreams | Trang thai cong viec | Danh sách ứng dụng, logistics, điều phối, commissioning, vị trí trống | area | "Manpower", "Applications", "Logistics & services", "Coordination" hoặc "Commissioning" (giữ đúng chữ)
|  |  | item | Hạng mục ("Vacant positions" là dòng vị trí còn trống)
|  |  | status | Trạng thái / bước tiếp theo
permits | Giay phep | Đăng ký giấy phép | permit | Tên giấy phép (không trùng)
|  |  | facility | Áp dụng cho
|  |  | authority | Cơ quan
|  |  | issue_date | Ngày cấp YYYY-MM-DD
|  |  | expiry_date | Ngày hết hạn YYYY-MM-DD
|  |  | renewal_date | Gia hạn trước YYYY-MM-DD
|  |  | status | "Issued", "Temporary", "Waiting…" hoặc ghi chú
precom_plan | Pre-com | Biểu đồ tiến độ pre-commissioning | activity | Tên hoạt động
|  |  | plan_start | Bắt đầu KH YYYY-MM-DD
|  |  | plan_finish | Kết thúc KH YYYY-MM-DD
|  |  | actual_start | Bắt đầu thực tế YYYY-MM-DD
|  |  | actual_finish | Kết thúc thực tế YYYY-MM-DD (có ngày → thanh màu xanh)
startup_sequence | Trinh tu khoi dong | Trình tự khởi động CPP | step | Số thứ tự
|  |  | phase | Tên bước
|  |  | action | Nội dung

## Thong tin
report_date | report_title | prepared_by
2026-10-21 | Operations Readiness Preparation | OPS Department

## Nhan su theo thang
month | onshore_plan | onshore_actual | offshore_plan | offshore_actual | total_plan | total_actual
2024-01 | 5 | 5 | 2 | 2 | 7 | 7
2024-02 | 5 | 5 | 2 | 2 | 7 | 7
2024-03 | 5 | 5 | 2 | 2 | 7 | 7
2024-04 | 5 | 5 | 2 | 2 | 7 | 7
2024-05 | 5 | 5 | 2 | 2 | 7 | 7
2024-06 | 5 | 5 | 2 | 2 | 7 | 7
2024-07 | 7 | 7 | 2 | 2 | 9 | 9
2024-08 | 8 | 8 | 6 | 6 | 14 | 14
2024-09 | 11 | 11 | 6 | 6 | 17 | 17
2024-10 | 13 | 13 | 6 | 6 | 19 | 19
2024-11 | 13 | 13 | 6 | 6 | 19 | 19
2024-12 | 13 | 13 | 6 | 6 | 19 | 19
2025-01 | 18 | 13 | 6 | 6 | 24 | 19
2025-02 | 18 | 13 | 6 | 6 | 24 | 19
2025-03 | 18 | 16 | 6 | 6 | 24 | 22
2025-04 | 19 | 16 | 6 | 6 | 25 | 22
2025-05 | 19 | 16 | 6 | 6 | 25 | 22
2025-06 | 20 | 18 | 6 | 6 | 26 | 24
2025-07 | 20 | 20 | 7 | 7 | 27 | 27
2025-08 | 20 | 20 | 7 | 7 | 27 | 27
2025-09 | 21 | 20 | 7 | 7 | 28 | 27
2025-10 | 21 | 20 | 7 | 7 | 28 | 27
2025-11 | 21 | 18 | 7 | 7 | 28 | 25
2025-12 | 21 | 19 | 7 | 8 | 28 | 27
2026-01 | 29 | 18 | 23 | 9 | 52 | 27
2026-02 | 29 | 19 | 23 | 16 | 52 | 35
2026-03 | 29 | 23 | 23 | 20 | 52 | 43
2026-04 | 33 | 24 | 35 | 25 | 68 | 49
2026-05 | 33 | 24 | 35 | 32 | 68 | 56
2026-06 | 33 | 28 | 35 | 36 | 68 | 64
2026-07 | 34 | 28 | 50 | 39 | 84 | 67
2026-08 | 34 | 29 | 88 | 42 | 122 | 71
2026-09 | 34 | 33 | 88 | 46 | 122 | 79
2026-10 | 34 | 32 | 88 | 47 | 122 | 78
2026-11 | 34 |  | 88 |  | 122
2026-12 | 34 |  | 88 |  | 122
2027-01 | 34 |  | 99 |  | 133
2027-02 | 34 |  | 99 |  | 133
2027-03 | 34 |  | 119 |  | 153
2027-04 | 34 |  | 131 |  | 165
2027-05 | 34 |  | 131 |  | 165
2027-06 | 34 |  | 131 |  | 165
2027-07 | 34 |  | 132 |  | 166
2027-08 | 34 |  | 132 |  | 166
2027-09 | 34 |  | 132 |  | 166
2027-10 | 34 |  | 132 |  | 166
2027-11 | 34 |  | 132 |  | 166
2027-12 | 34 |  | 132 |  | 166
2028-01 | 34 |  | 132 |  | 166
2028-02 | 34 |  | 132 |  | 166
2028-03 | 34 |  | 132 |  | 166
2028-04 | 34 |  | 132 |  | 166
2028-05 | 34 |  | 132 |  | 166
2028-06 | 34 |  | 132 |  | 166
2028-07 | 34 |  | 132 |  | 166
2028-08 | 34 |  | 132 |  | 166
2028-09 | 34 |  | 132 |  | 166
2028-10 | 34 |  | 132 |  | 166
2028-11 | 34 |  | 132 |  | 166
2028-12 | 34 |  | 132 |  | 166

## Dinh bien
group | filled | required
Onshore | 32 | 34
Offshore | 47 | 50
Outsource | 9 | 38

## CBTA
platform | team | modules | developing | review | completed | theory_pct | ojt_modules | ojt_pct
CPP | P&P | 36 | 6 | 1 | 27 | 3.87 | 36 | 0
CPP | E&I | 39 | 1 |  | 35 | 7.85 | 39 | 0
CPP | M&R | 38 | 6 | 1 | 27 | 1.48 | 38 | 0
CPP | Deck crew | 11 | 0 | 0 | 11 | 6.25 | 11 | 0
WHP | P&P | 21 | 0 | 0 | 21 | 0 | 29 | 0
WHP | E&I | 24 | 2 | 2 | 20 | 0 | 35 | 0
WHP | M&R | 22 | 0 | 1 | 21 | 0 | 31 | 0

## Dao tao bat buoc
team | planned | earned | balance
Management | 263 | 72 | 191
CPP P&P | 334 | 195 | 139
CPP M&R | 210 | 92 | 118
CPP E&I | 270 | 96 | 174
CPP Deck crew | 72 | 19 | 53
WHP team | 250 | 130 | 120

## Dao tao vendor
course | period
ICSS – EPCI#2 | 2026-09
Asset Integrity Management | 2026-10
E-house | 2026-10
Gas Conditioning and Processing – G-4 | 2026-10
ICSS – EPCI#1 | 2026-11
Gas Purification Technology: Mercury Removal | 2026-11
ICSS – EPCI#1 | 2026-12
E-house | 2026-12
Telecom System (CPC0-TEL001) | 2027-01
HVAC system (MEL 41 – HVAC) | 2027-03
Mark CS O&M | 2027-04
Analyser – Water in Oil & Gas Chromatography (CPC0-ICS017) | 2027-04
Metering Skid (CPPT-ICS001) | 2027-05
Analyser – Moisture & Reid Vapor (CPC0-ICS031) | 2027-05
ECPI#2 – Gas booster compressor | 2027-11
EDG (CLQU-MEC005) | 2027-12
Gas Turbine Generator (GTG, MER 02) | 2028
Turbo Expander (CPPT-MEC003) | 2028
Vapour Recovery Compressor (CPPT-MEC005) | 2028

## ORR theo team
team | weight_pct | total_activities | completed | plan_pct | actual_pct | plan_end_pct
Offshore | 25.5 | 89 | 57 | 69.5 | 76.8 | 99
Production OPS | 13.2 | 59 | 23 | 71.3 | 66.5 | 98
Asset Integrity | 11.2 | 53 | 20 | 45.6 | 64.4 | 89
Manager OPS | 12.5 | 80 | 57 | 77.1 | 70.6 | 94
E&I | 9.1 | 32 | 21 | 65.7 | 79.4 | 82
M&R | 8.7 | 48 | 25 | 70.6 | 63.9 | 98
Application Eng | 6.9 | 28 | 10 | 67 | 71.3 | 96
Marine | 6.8 | 49 | 27 | 71.9 | 71.1 | 95
Production Eng | 6 | 36 | 14 | 60.6 | 57.3 | 99

## ORR theo thang
month | plan_pct | actual_pct
2026-10 | 67.2 | 70.5
2026-11 | 71
2026-12 | 75
2027-01 | 80
2027-02 | 83
2027-03 | 87
2027-04 | 90
2027-05 | 93
2027-06 | 95

## ORR hang muc
group | code | element | items | progress_pct
PEOPLE | PE-01 | Organization, Manning & Accountability | 14 | 64.3
PEOPLE | PE-02 | Competency, Training & Authorization | 26 | 59.9
PEOPLE | PE-03 | Personnel Mobilization & Fitness for Duty | 3 | 83.7
PEOPLE | PE-04 | HR Policies, Employment Conditions & Retention | 5 | 100
PLANT | PL-01 | Facilities, Process & Utilities Readiness | 11 | 77.2
PLANT | PL-02 | Wells, Flowlines & Export Systems Readiness | 20 | 80.2
PLANT | PL-03 | Asset Integrity & Safety Barrier Readiness | 8 | 14.1
PLANT | PL-04 | Spares, Materials, Consumables & Tools Readiness | 15 | 61.8
PLANT | PL-05 | Metering, Sampling, Analysers & Environmental Monitoring | 2 | 0
PLANT | PL-06 | Onshore Base, Port & Support Infrastructure | 4 | 72.3
PROCESS | PR-01 | ORR Governance, Readiness Acceptance & Financial Readiness | 18 | 85.8
PROCESS | PR-02 | Legal Compliance, Licences, Permits, Certification & Security | 20 | 81.5
PROCESS | PR-03 | HSE, Process Safety & Control of Work | 104 | 85.6
PROCESS | PR-04 | Emergency Response, Crisis Management & Continuity | 29 | 49.3
PROCESS | PR-05 | Operations Management & Production Chemistry | 80 | 45.4
PROCESS | PR-06 | Maintenance, Reliability & Integrity Management | 88 | 63.6
PROCESS | PR-07 | Contracts, Procurement & Supply Chain | 51 | 59.4
PROCESS | PR-08 | Integrated Coordination, Gas Dispatch, Metering & Commercial Interface | 13 | 41.5
PROCESS | PR-09 | Technical Information, Data, Digital Systems & OT Security | 40 | 59.6
PROCESS | PR-10 | Commissioning Interface, Handover, Start-up & Stabilization | 27 | 58.5
PROCESS | PR-11 | Production Management, Well Surveillance & Hydrocarbon Accounting | 21 | 70.1
PROCESS | PR-12 | Marine, Aviation & Logistics Operations | 49 | 68.8
PROCESS | PR-13 | Performance Management, Assurance & Continuous Improvement | 22 | 68
PROCESS | PR-14 | Design, Engineering, Operability & Maintainability Assurance | 22 | 89.3

## ORR tong nhom
group | items | progress_pct
PEOPLE | 48 | 66.3
PLANT | 60 | 61.4
PROCESS | 590 | 66
TOTAL | 698 | 65.6

## Quy trinh
id | category | document | level | issued | responsible | expected | completion_pct | remark
HSE-01 | HSE | Permit to Work Procedure | Company | Yes | Offshore | Jan-25 | 100 | Issued on 25-Mar-25
HSE-02 | HSE | Equipment Isolation Philosophy | Company | Yes | Offshore | Jan-25 | 100
HSE-03 | HSE | Lock-out Tag-out Procedure | Company | Yes | Offshore | Jan-25 | 100 | Issued
HSE-04 | HSE | Hot work control procedure | Department | Yes | Offshore | Jan-25 | 100 | Issued on 25-Mar-25
HSE-05 | HSE | Respirator Protection procedure | Department | Yes | Offshore | Mar-25 | 100 | Issued 09 Jun 25
HSE-06 | HSE | HV/MV procedure | Department | Yes | Kiet HT | Mar-25 | 100 | Issued
HSE-07 | HSE | ToolBox Talk procedure | Company | Yes | Offshore | Mar-25 | 100 | Issued on 17 Jan 25
HSE-08 | HSE | Electrical Code of Practice | Company | Yes | Kiet HT | Jun-26 | 100 | Issued
HSE-09 | HSE | H2S procedure | Company | Yes | Offshore | Mar-25 | 100 | Issued
HSE-10 | HSE | Scaffolding Procedure | Department | Yes | Offshore | Mar-25 | 100 | Issued on 22/01/25
HSE-11 | HSE | Electrical safety procedure | Department | Yes | Kiet HT | Mar-25 | 100 | Issued on Oct 24
HSE-12 | HSE | Marine Operations Manual | Department | Yes | Thanh NN | Mar-25 | 100 | Issued
HSE-13 | HSE | Working at Height Procedure | Department | Yes | Offshore | Apr-25 | 100 | Issued on 22/01/25
HSE-14 | HSE | Overside Working Procedure | Department | Yes | Offshore | Apr-25 | 100 | Issued on 22/01/25
HSE-15 | HSE | Pressure and Leak Testing Procedure | Department | Yes | Offshore | May-25 | 100 | Issued
HSE-16 | HSE | Compressed Air procedure | Department | Yes | Offshore | May-25 | 100 | Issued on 22/01/25
HSE-17 | HSE | Noise exposure and hearing protection | Department | Yes | HSE Onshore | Dec-25 | 100 | Issued
HSE-18 | HSE | Vibration Impact procedure | Department | Yes | Offshore | May-25 | 100 | Issued on 15 Feb 25
HSE-19 | HSE | Catering food safety & hygiene management procedure | Department | Yes | Offshore | Jun-25 | 100 | Issued
HSE-20 | HSE | Mercury Hazard Control Procedure | Department | Yes | Nguyen Minh Hoang | Jun-25 | 100 | Issued
HSE-21 | HSE | HSE Risk Management Procedure | Department | Yes | Offshore | Jun-25 | 100 | PQ1-00-HSE-PCD-PQC-00004-00_H01
HSE-22 | HSE | Tools and Equipment Procedure | Department | Yes | Offshore | Jul-25 | 100 | Issued on 15 Feb 25
HSE-23 | HSE | Confined Space Entry Procedure | Department | Yes | Offshore | Jun-25 | 100 | Issued
HSE-24 | HSE | HSE Recording and Reporting Guideline | Company | Yes | Offshore | Jun-26 | 100 | Issued
HSE-25 | HSE | Inspection and Certification of Lifting Equipment | Department | Yes | Nguyen TN | Jun-26 | 100 | Issued
HSE-26 | HSE | Portable Appliance Testing Procedure | Department | Yes | Kiet HT | Jun-26 | 100 | Issued
HSE-27 | HSE | Gas Testing procedure | Department | Yes | Offshore | Jun-25 | 100 | Issued on 17 Jan 25
HSE-28 | HSE | Offshore facility procedure | Department | Yes | Offshore | Jun-25 | 100 | Issued on 15 Feb 25
HSE-29 | HSE | Simultaneous Operations procedure (SIMOP) | Department | No | Offshore HSE | Dec-26 | 75 | Review ongoing
HSE-30 | HSE | Emergency response plan for supply vessels | Department | Yes | Thanh NN/HSE | Dec-26 | 100 | Included in vessel service contract
HSE-31 | HSE | Domestic Water Control & Monitoring | Department | Yes | Offshore/HSE | Jul-25 | 100 | Issued
HSE-32 | HSE | POB List and control procedure incl. T-Card control | Department | Yes | Offshore | Jul-25 | 100 | Issued
HSE-33 | HSE | Radio Silence Procedure | Department | Yes | Drilling Dep | Aug-25 | 100 | Issued
HSE-34 | HSE | Safety Standdown Procedure | Department | Yes | Offshore | Jun-26 | 100 | Issued
HSE-35 | HSE | Emergency response Procedure for HUB/WHP | Department | No | HSE Onshore | Apr-27 | 0 | Bid submission deadline extended to 13 Oct 2026
HSE-36 | HSE | Operating and guideline for Security vessel | Department | Yes | Thanh NN | Oct-25 | 100 | Issued
HSE-37 | HSE | Management of Change Procedure | Company | Yes | Ngoc NV | Dec-25 | 100 | Issued
HSE-38 | HSE | Emergency response Procedure for CPP complex | Department | No | HSE Onshore | Apr-27 | 0 | Bid submission deadline extended to 13 Oct 2026
HSE-39 | HSE | Operation Performance Standard | Department | No | Onshore | Dec-26 | 90 | Completed for ECP2; ECP1 in EDMS for review
HSE-40 | HSE | Pressure cylinder management Procedure | Department | Yes | Offshore | Dec-26 | 100 | Issued
GEN-01 | General operations | Use and inspection of utility hoses and fittings | Department | Yes | Offshore | Jun-25 | 100 | Issued on 13 Feb 25
GEN-02 | General operations | Offshore Crane Operating and Maintenance Guideline | Department | Yes | Offshore | Jun-25 | 100 | Issued
GEN-03 | General operations | Mooring Guidelines at PQPOC field | Department | No | NN Thanh | Dec-26 | 0 | Waiting for mooring system
GEN-04 | General operations | Fast Rescue Craft (OSV) | Department | Yes | NN Thanh | Jun-25 | 100 | In Marine Operations Manual (section 8.13)
GEN-05 | General operations | Portable and Temporary Equipment Procedure | Department | Yes | Offshore | Jun-25 | 100 | Issued on 13 Feb 25
GEN-06 | General operations | Safety Standby/Lifting Support Vessel Operations | Department | Yes | NN Thanh | Jul-25 | 100 | In Marine Operations Manual (section 8)
GEN-07 | General operations | Handover Guidelines for Personnel at Crew & Shift Changes | Department | Yes | Offshore | Aug-25 | 100 | Issued
GEN-08 | General operations | Maintenance, inspection, repair & overhaul of electrical installations in Hazardous Areas | Department | Yes | Anh HT Kiet | Sep-25 | 100 | Issued
GEN-09 | General operations | Well Handover Procedure | Department | Yes | DCD | Sep-25 | 100
GEN-10 | General operations | Instrument Calibration Procedure | Department | Yes | Offshore | Sep-25 | 100 | Issued
GEN-11 | General operations | Well Integrity Procedure | Department | Yes | DCD | Sep-25 | 100 | Issued
GEN-12 | General operations | Errant Vessel Response Procedure | Department | Yes | NN Thanh | Sep-25 | 100 | Issued
GEN-13 | General operations | Fuel management and bunkering procedure | Department | No | NN Thanh | Dec-26 | 75 | Ongoing
GEN-14 | General operations | Platform Standing Instruction | Department | Yes | Offshore | Dec-26 | 100 | Issued on 13 Feb 25
GEN-15 | General operations | Shutdown and start up procedure including field start up | Department | No | Offshore | Dec-26 | 60 | Ongoing
GEN-16 | General operations | E&I Tools Re-Certification Procedure | Department | Yes | HT Kiet | Dec-26 | 100 | Issued
GEN-17 | General operations | Coating Maintenance & Repair Procedure | Department | Yes | Offshore | Jan-26 | 100 | Issued
GEN-18 | General operations | CPP Export Gas Metering procedure | Department | No | Anh HT Kiet + Offshore | Dec-26 | 0 | DX lead to work with Biên
GEN-19 | General operations | Controlled Gas Offspec Procedure | Department | No | Offshore + Thuy | Dec-26 | 50 | Ongoing
GEN-20 | General operations | Hot bolting procedure | Department | Yes | Offshore | Jun-26 | 100 | Issued 27 May 25
GEN-21 | General operations | Housekeeping Guidelines | Department | Yes | Offshore | Dec-26 | 100 | Issued on 11 Jan 25
GEN-22 | General operations | Lifeboat Launching Recovery and Stowage | Department | No | NN Thanh | Dec-26 | 50 | Waiting for lifeboat manual from vendor
GEN-23 | General operations | Laboratory Operations General | Department | Yes | Thuy + Offshore | Dec-26 | 100 | Issued
GEN-24 | General operations | Lab sampling and Testing | Department | No | Thuy + Offshore | Dec-26 | 65 | Preparation ongoing
GEN-25 | General operations | Control Override / Bypass / Suppression Management | Department | Yes | HT Kiet + Offshore | Dec-26 | 100 | On E-office
GEN-26 | General operations | Alarm & Trip Setting Procedure | Department | Yes | HT Kiet + Thuy | Dec-26 | 100 | Issued
GEN-27 | General operations | Pigging and batch pigging procedure | Department | No | Guy NT | Dec-27 | 0 | Discussing with potential vendors (Rosen, TDWilliamson, …)
GEN-28 | General operations | Pressure Safety Valve Testing and Recertification | Department | Yes | TN Nguyen | Jan-27 | 100 | Issued
GEN-29 | General operations | E&I CFT | Department | Yes | E&I Sup | Jan-27 | 100 | Issued
GEN-30 | General operations | WH CFT | Department | No | WH Sup | Jan-27 | 75 | Reviewing
GEN-31 | General operations | P&P Critical Function Testing | Department | No | Offshore | Jan-27 | 75 | Reviewing

## Goi chua co PR
dimension | category | count
status | Open | 19
status | PR Request | 7
status | Screening | 7
priority | Priority 1 | 3
priority | Priority 2 | 8
priority | Priority 3 | 15
scr_timing | This month | 1
scr_timing | Next month | 2
scr_timing | Not set | 16

## PR dang xu ly
stage | status | count
1 CSP Preparation | Near-late | 1
1 CSP Preparation | On time | 1
2 CSP Approval | Late | 1
2 CSP Approval | On time | 1
3 Bidding | Near-late | 1
3 Bidding | On time | 1
4 Evaluation | Late | 1
4 Evaluation | On time | 2
5 TCEAR Approval | Late | 1
6 Contract Signing | On time | 1

## CMMS
package | actual_pct | plan_pct
EPCI#2 | 82.11 | 85
EPCI#1 | 41.58 | 42.3

## Trang thai cong viec
area | item | status
Manpower | Vacant positions | Document Control, OIM, HSE, FSO
Applications | PDMS | Technical evaluation
Applications | AIMS | TCEAR
Applications | OSCC | ITB
Applications | HRIS | Platform built (production launch); preparing test and data population
Applications | EAM/SAP | Training and UAT phase 2 completed (Plant maintenance, Inventory & Warehouse); preparing phase 3 kick-off (KPI, reports)
Applications | OMS | Phase 1 blueprint completed; platform development continuing
Logistics & services | Helicopter | Combine with DCD's contract
Logistics & services | Supply vessel, FCB, security boat | ITB
Logistics & services | Vessel inspection | Combine with DCD to 2030
Logistics & services | MGO | Change to contract
Logistics & services | Crew change service to Nam Can | Raise PIA, PR
Logistics & services | Catering services | No update in report
Coordination | Coordination procedure | Being split into 2 procedures; parties to review and complete by 31 Oct
Coordination | Production profile | Sales gas capability 73 MMscfd (SSF) from Sep-27, rising to about 170 MMscfd (75%) by Nov-27 vs total sales gas requirement
Commissioning | Offshore preservation | Findings → punch list → close out
Commissioning | Installation, pre-com, com | E-house, HVAC, Crane, FM200, LQ UPS

## Giay phep
permit | facility | authority | issue_date | expiry_date | renewal_date | status
Frequency certificate for FSO DMR (CPP) | CPP – FSO | Radio Frequency Authority (ARFM) | 2025-07-31 | 2028-07-30 | 2028-02-01 | Issued
Frequency certificate for FSO DMR (LQ) | LQ – FSO | Radio Frequency Authority (ARFM) | 2025-07-31 | 2028-07-30 | 2028-02-01 | Issued
UHF radio frequency license | CPP | Radio Frequency Authority (ARFM) | 2025-07-21 | 2028-07-20 | 2028-01-22 | Issued
Frequency licenses for temporary DMRs | AQWA, KLWA, KLWB, CVWA | Radio Frequency Authority (ARFM) | 2025-08-13 | 2027-08-12 |  | Temporary
Frequency license for VHF Airband (CPP, LQ) | CPP, LQ | Radio Frequency Authority (ARFM) |  |  |  | Waiting for helideck license
Frequency license for NDB (LQ) | LQ | Radio Frequency Authority (ARFM) |  |  |  | Waiting for helideck license
FSO certificate (class & flag state) | FSO | PPS |  |  |  | No update in report
Helideck operation approval | Helideck | MM Marine |  |  |  | No update in report
ISPS | Marine | MM Marine |  |  |  | No update in report
Port license | Marine | MM Marine |  |  |  | No update in report

## Pre-com
activity | plan_start | plan_finish | actual_start | actual_finish
Pre-commissioning Hydraulic Power Unit (with TUTU) (CPPT-04-01) | 2027-01-04 | 2027-01-13
Pre-commissioning Inlet Separators Train 1 (CPPT-10-01) | 2027-01-06 | 2027-01-23
Pre-commissioning Production & Pipeline Compressor Train 1 (CPPT-11-01) | 2026-12-15 | 2026-12-25
Pre-commissioning Production Compressor Suction Train 1 (CPPT-11-02) | 2026-12-03 | 2026-12-12
Pre-commissioning Production Compressor Discharge Train 1 (CPPT-11-03) | 2027-01-05 | 2027-01-08
Pre-commissioning Gas Turbine Lube Oil Train 1 (CPPT-11-04) | 2026-10-13 | 2026-11-16
Pre-commissioning UCP for Production & Pipeline Compressor Train 1 (CPPT-11-05) | 2026-11-16 | 2026-12-08
Comm Train 1 – Production & Pipeline Compressor System (FTP) | 2027-01-09 | 2027-02-19
Pre-commissioning Glycol Dehydration Train 1 (CPPT-12-01) | 2027-01-04 | 2027-01-23
Pre-commissioning Glycol Regeneration Train 1 (CPPT-12-02) | 2026-11-02 | 2026-11-19
Comm Train 1 – Glycol Regeneration (FTP) | 2027-01-25 | 2027-02-26
Pre-commissioning Expander Suction Train 1 (CPPT-13-01) | 2026-10-31 | 2026-11-13
Pre-commissioning Turbo Expander Package Train 1 (CPPT-13-02) | 2026-10-31 | 2026-11-11
Pre-commissioning Expander Discharge Train 1 (CPPT-13-03) | 2026-10-31 | 2026-11-13
Pre-commissioning Booster Compressor Suction & Discharge Train 1 (CPPT-13-04) | 2026-11-14 | 2026-11-23
Pre-commissioning Turbo Expander Lube Oil Cooler Train 1 (CPPT-13-05) incl. oil flushing | 2026-10-31 | 2026-11-23
Pre-commissioning UCP – Turbo Expander Package Train 1 (CPPT-13-06) | 2026-10-17 | 2026-10-26

## Trinh tu khoi dong
step | phase | action
1 | Preparation | Dewater and purge export gas pipelines; purge process systems; start LQ emergency DG for power; start LQ air compressor
2 | Start up CPP | Start 1 GTG on diesel mode; start CPP air compressor
3 | First well | Open 1st AQWA well to test separator; pressurize AQWA process; drain completion liquid to sea
4 | Pressurize CPP | Route gas and liquid to CPP; pressurize CPP and flare tower; route liquid to liquid separation system
5 | Gas & fuel gas | Route gas to gas system and start fuel gas system (purging/blanket gas, fuel gas, chemical system)
6 | Second well | Open 2nd AQWA well to test; switch 1st well out of test
7 | GTG to fuel gas | Switch GTG to fuel gas; start 2nd GTG on fuel gas; start glycol regeneration and hot oil systems in cold circulation
8 | Third well | Open 3rd AQWA well; switch 2nd well out of test and 3rd well to test
9 | Ramp up wells | Open 4th–7th wells on AQWA, then 8th well and re-open other wells
10 | GTC & WHRU | Start GTC in circulation mode; start WHRU to heat hot oil and glycol regeneration
11 | Dew point | Start dew point system (JT valve); open MRU bypass; switch dew point from JT valve to expander unit if needed
12 | MRU | Start MRU; close bypass line when gas dew point is on spec
13 | Export gas | Export gas to export gas pipeline
14 | Condensate & PW | Condensate to stabilizer in circulation (VRU recycle at turndown), export to FSO when on spec; produced water injected into AQWA wells if on spec, off-spec to FSO